Annual Report 2006

CVCTC+ THENI

The project titled "Challenging AIDS related poverty" being implemented by south India AIDS Action Program, a leading non governmental organization functioning for the well being of marginalized communities of southern region of India. The organization act as a coordinating agency for the project which was implemented with help of 8 coalition partners of 5 highest HIV prevalence states of India. The project at Theni district was implemented by a self help group of marginalized community named as Periyakulam AIDS Thaduppu Matrum Magalir Munnetra Sangam with the facilitation of Siaap. The community based service facility CVCTC+ was established in Theni to build capacities of self help groups of marginalized communities and CSO networks to facilitate them to advocate against stigma and discrimination and to ensure the equitable access to the needed services. The site for CVCTC was identified by the Directors of sangam which they think that it is a more ideal place to access the services by target community. CVCTC is a tool by which the activities like mobilizing the target community, sensitizing the environment, advocacy, care and support services could be carried out.

Overall Objectives of the project

Reduce poverty and improve quality of life of poor and traditionally marginalized communities disproportionately affected by or vulnerable to HIV/AIDS, and empower civil society organizations to check the spread of HIV and reduce the impact of AIDS.

Specific Objective

Reduce stigma and discrimination and increase equitable access to HIV/AIDS prevention and treatment, care and support, for the people in sex work(PSW), gay, bisexual, Transgender and transsexual people living with HIV/ AIDS and their families and people living in immediate   environment of the target communities (PIE), through establishing community based voluntary counseling, testing , support and care centers(CVCTC+) and promoting self help groups of members of target communities to addresses the sociological, psychological and medical factors that increase the vulnerability to HIV/AIDS

Progress against Expected Results

Expected Result 1:

Improved quality of life of PSW, GBT, PLHA and PIE through improved health seeking behavior and equitable access to services through community based voluntary counseling testing support and care centers (CVCTC+).

Work Plan Activity 1.1: Establishment and operationalisation of community based voluntary counseling, testing, support and care centers (CVCTC+) as hubs to promote health seeking behavior and to advocate against stigma and discrimination.

Highlights

- Site for CVCTC+ identified by sangam.

- Outreach workers and counselor recruited by sangam.

- Building maintenance work done.

- Equipment and materials procured for operation.

- Staff attended trainings to develop knowledge and skills.

- Doctors identified for the position of medical officer.

- Office assistant was appointed.

As the project only aims for the well being of poor and marginalized communities, contribution of those communities is vital to achieve the objective of the program. The nature of project and the courses of action which is to be taken were elaborately discussed with sangam Directors and members before they decide to own the project. The site to set up CVCTC+ is decided by sangam and made notable effort to identify a rental building at Theni town. The people from various of  the district comes to Theni in regular interval for purchases, to access treatment and others, also Theni is a intersection point for people wants to travel within and outside the district. So the Sangam members made a decision to set up the CVCTC+ near to Theni bus stand. It becomes more accessible.

The applications were collected from the candidates belongs to community for outreach work. The sangam members recruited the candidates with the facilitation of project staff on the basis of the criteria like literacy, communication skill and attitude towards community. Four candidates were selected and trained on basic facts about HIV/AIDS, but two of them were refused to work. As per the suggestion of PMC, a community counselor was appointed by sangam on 11.08.2006.

The office assistant was appointed on 16.06.2006.

When the building was rented, it was not in the state for operation. The building maintenance work was carried out during the period of 15.04.2006 to 09.06.2006 and the building became favorable to offer services. The physical equipments and materials needed for testing and treatment was procured. With this CVCTC+ was getting ready for operation if the test kits made available. On the view of sustaining the project, board of directors of Siaap suggested to utilize the existing services for testing that is "collecting the blood samples at the centre and test it in the lab of nearest ICTC"  established by Tamilnadu state AIDS control society. Though several attempts were made by our organization to obtain permission from TNSACS, not yet got the written permit. An alternative to this, BOD recommended to procure test kits tentatively from APAC and it was done.

Once the APAC granted permission to supply test kits, the project team have made efforts to find doctors in and around for the position of medical officer in the centre. 11 doctors were approached in this regard. Among them, two were expressed their willingness to spend time for our CVCTC+ in morning hours. The efforts are under process to recruit a doctor. CVCTC+ will start its function by providing counseling, treatment delivery services once the medical officer is appointed.

Siaap have organized capacity building programs for the team members in regular interval to equip their knowledge, skills and attitude. The programs were very useful for the team members to understand the concept of the project, the series of action to be carried out to achieve the objective of the project. The events like training program and quarterly review meeting helps the team to express the progress of the project and to get suggestions to improve the level of activities of centre by sharing  experiences each other.

Table 1

List of capacity building programs attended by team members

| Sl.No. | Date | No. of Days | Title of the Program. | Venue | Participants |
| --- | --- | --- | --- | --- | --- |
| 1 | 17,18.03.2006 | 2 | Orientation program | Periyakulam sangam | Project officer, Outreach workers, Lab Technician |
| 2 | 24-28.04.2006 | 5 | Foundation Training | Life Health centre for Handicapped. Chennai. | Project officer, Accountant, Outreach workers and Lab Technician. |
| 3 | 29.06.2006-01.07.2006 | 3 | Training on research of Baseline survey | Asha Nivas social welfare centre. Chennai | Project officer |
| 4 | 03.10.2006 | 1 | Training on accounts | Siaap | Accountant |
| 5 | 28.10.2006 | 1 | Exposure visit | WINS, Thirupathi. | Project officer, Counselor. |
| 6 | 05.11.2006 | 1 | Training on philosophy and vision building-CVCTC+ | Siaap, Chennai. | Project officer |
| 7 | 06-08.11.2006 | 3 | Training on Treatment Education | Asha Nivas social welfare centre. Chennai | Project officer, Counselor, Outreach worker. |
| 8 | 21,22.11.2006 | 2 | BLS dissemination workshop | International Research Centre for Pilgrimage, St.Thomas Mount. | Project Officer |

Work Plan Activity 1.2 : Sensitization and mobilization of target communities in project area to access CVCTC+ and other existing services.

Highlights

- Target communities identified and established rapport.

- SHG women covered by village education programs.

- Set up awareness stall.

- Target community started accessing the centre.

- Started delivering counseling and referral services.

- Adopted various methods for condom promotion.

As the sexuality and sexual behavior of the marginalized communities those who are more vulnerable to HIV/AIDS is being depicted as unusual behavior, they are discriminated by the society. People belongs to the communities hesitates to disclose their identity which make the outreach workers feel very hard to identify, establish rapport and motivate them to access the services. A strategy known chain system which was adopted by many business concerns to market their products, used in our outreach work by which a outreach worker will establish better relationship with a well known person (belongs to community) who helps to identify the new people those who are familiar to them. By this approach, 441(74 villages) people were identified, established rapport and being motivated to access the services.

Table 2

List of target communities covered by outreach work

| Month | FSW | MSM/TG | PLHA | Total |
| --- | --- | --- | --- | --- |
| April | 47 | 6 | 16 | 69 |
| May | 45 | 11 | 15 | 71 |
| June | 56 | 10 | 15 | 81 |
| July | 77 | 4 | 14 | 95 |
| August | 32 | 0 | 0 | 32 |
| September | 46 | 0 | 0 | 46 |
| October | 21 | 2 | 0 | 23 |
| November | 24 | 0 | 0 | 24 |
| Total | 348 | 33 | 60 | 441 |

The village education programs being organized for the members of self help groups for the purpose of generating awareness on basic facts about HIV/AIDS and motivate them to support marginalized communities to advocate for their needs. The details of self help groups was collected by outreach worker during their field visit and develop plan to organize meeting for women group members accordingly. Mostly the outreach workers plan to organize the education program according to the convenience of the group (during the hours of their regular monthly meetings.). Most of the participants felt free to ask their doubts and enthusiastic during the session. The details of 339 SHG's were collected from 31villages and the village education program was organized in 13 villages and covered 472 members of 43 SHG's by 22 events.

Table 3

Details of village education programs

| Month | No of Events | No of SHG's | No of participants |
| --- | --- | --- | --- |
| August | 4 | 14 | 98 |
| September | 10 | 13 | 198 |
| October | 4 | 8 | 85 |
| November | 4 | 8 | 91 |
| Total | 22 | 43 | 472 |

Though several steps has been taken by various intervention programs, still the rate of HIV prevalence is increasing as no services available and accessible to protect from contracting the virus. The people not prefer to buy condoms in outlets and feel guilty for that act because of internalization of social values. Our condom promotion strategy was framed in the view of resolving the above said problem. The condom boxes (6) were installed in 4 public toilets located in Theni, Bodi and Periyakulam bus stands from which 2450 condoms were distributed. 413 condoms were taken from trays placed in the centre. There are 1110 condoms directly distributed to the target communities by outreach work. These methods are easy to access by the target communities.

Table 4

Details of condoms distributed from condom boxes and Tray

|  | Condom Boxes |  | Condom Tray |
| --- | --- | --- | --- |
| Month | No of Boxes | No of Condoms distributed | No of condoms distributed |
| August |  |  | 183 |
| September |  |  | 30 |
| October | 2 | 500 | 100 |
| November | 6 | 1950 | 100 |
| Total | 8 | 2450 | 413 |

Table 5

Details of condoms directly distributed by outreach work

|  |  | Classification of Beneficiaries |  |  |
| --- | --- | --- | --- | --- |
| Month | No of condoms distributed | FSW | PIE | MSM/TG |
| August | 340 | 18 | 5 | 4 |
| September | 330 | 25 | 6 | 1 |
| October | 190 | 13 | 0 | 0 |
| November | 250 | 13 | 0 | 0 |
| Total | 1110 | 69 | 11 | 5 |

The efforts was made for the promotion of the services offered by our centre by set up awareness stall in weekly market of Theni where people from almost all parts of the district gather on every Sunday. 424 people visited and distributed 1267 IEC materials distributed (procured from TNSAC) and 1815 condoms. The services of the centre explained to the visitors by our stall in-charge. Though the stall was set up at the market 3 times, no visitors of the stall accessed our CVCTC+ by the first two events. But the people started accessing the centre after the last event. 5 persons were accessed and offered counseling for 4 and referred 3 for HIV screening to the nearest ICTC. The visitor particulars fed into system to sort out places from where most of visitors accessed the stall and it helps to concentrate more on the respective places by field level activities.

Details of people visited and IEC and Condom distributed in awareness stall.

Table 6

Details of Awareness Stall

| Month | Events | No of Visitors | No of IEC distributed | No of condom distributed |
| --- | --- | --- | --- | --- |
| October | 2 | 323 | 955 | 1440 |
| November | 1 | 101 | 312 | 375 |
| Total | 3 | 424 | 1267 | 1815 |

Though, the testing and treatment delivery services are unavailable in our centre, 190 people were visited, 22 were counseled and referred 5 for HIV testing to the ICTC located in Holy Redeemer Hospital. 11 Condom demonstrations were done and 235 condoms were given to 25 clients by the counselor.

Table 7

Details of visitors to CVCTC+

|  | New Visitors |  | Repeat Visitors |  |  |
| --- | --- | --- | --- | --- | --- |
| Month | Male | Female | Male | Female | Total |
| June | 0 | 1 | 2 | 7 | 10 |
| July | 1 | 0 | 3 | 3 | 7 |
| August | 0 | 3 | 5 | 0 | 8 |
| September | 1 | 6 | 13 | 20 | 40 |
| October | 4 | 43 | 9 | 16 | 72 |
| November | 4 | 12 | 24 | 13 | 53 |
| Total | 10 | 65 | 56 | 59 | 190 |

Table 8

Details of counseling and referral

|  | Counseling |  | Referral |  |
| --- | --- | --- | --- | --- |
| Month | FSW | Male | FSW | Male |
| September | 9 | 4 | 0 | 1 |
| October | 1 | 1 | 1 | 1 |
| November | 1 | 6 | 0 | 3 |
| Total | 11 | 11 | 1 | 5 |

Table 9

Condom demonstration and distribution by Counselor

| Month | Condom Demonstration | No of Beneficiaries FSW Male |  | No of condoms distributed |
| --- | --- | --- | --- | --- |
| September | 6 | 2 | 8 | 100 |
| October | 3 | 6 | 3 | 65 |
| November | 2 | 3 | 3 | 70 |
| Total | 11 | 11 | 14 | 235 |

Expected Result 2: An effective alliance of 16 groups of target communities of PSW's ,GBT, PLHA and coalition members engaged in community mobilization and advocacy at government, private and community levels to reduce stigma and discrimination.

Work plan activity 2.1: Baseline survey in specific project areas to quantify existing levels stigma and discrimination, among target communities.

Highlights

- Collected necessary secondary data.

- Baseline survey conducted among target communities.

- Resolution against S&D passed in villages.

The process of secondary data collection was initiated from the beginning of the project period to understand the geographical characteristics of the target area. It was useful to plan our centre level activities. The following data collected from different sources.

Table 10

Data and Sources

| Sl.No. | Data | Sources |
| --- | --- | --- |
| 1 | List of Primary health centers and contact no's | DDHS |
| 2 | Geographical map of Periyakulam,Theni and Bodi | Department of statistics, Collectorate |
| 3 | Town panchayats, municipalities and its population. | Website |
| 4 | Village wise population | Village Panchayat office, Jeyamangalam. |
| 5 | Reproductive age wise population | Website |
| 6 | Details of ICTC | ICTC, Uthamapalayam |
| 7 | List of ANC accessed Uthamapalayam Taluk Hospital | ICTC, Uthamapalayam |
| 8 | List of Anganvadi centers in Theni Union | ICDS office, Theni. |
| 9 | List of Anganvadi centers in all Municipalities | ICDS District Program Office, Theni. |
| 10 | List of ANC mothers in Theni town and nearest villages | Anganvadi centers |

The baseline survey was conducted with the guidelines of Community Advisory Board in order to understand the existing level of stigma and discrimination faced by the marginalized communities mainly FSW's and PLHA. The advocacy plan and other efforts can be developed according to the findings of the study. The qualitative and quantitative methods, FGD and individual interview respectively used to collect data from the community. The individual interview was conducted among 25 FSW and 25 PIE. The FGD's, 3 among FSW, 2 among PLHA and 1 among PIE were conducted. As the findings of the study shows that 89% of people expressed fear of contracting HIV by casual contact and only 47% of respondents are aware about all modes of HIV transmission, we plan to emphasize more on these areas in village education meetings and outreach work. According to the result of the study, we plan our advocacy strategies in discussion with other coalition partners and self help group of target communities to reduce stigma and discrimination and mobilize the marginalized communities to access the services.

Without having any empirical evidence of S& D in the target area, the resolution against stigma and discrimination faced by people living with HIV/AIDS was passed in Gram Saba meetings of the village panchayats. It was passed by panchayat president, ward members and other representatives of public that they will not stigmatize and discriminate the people living with HIV/AIDS in their gram panchayats. In addition, the event was useful to provide information about CVCTC+ and establish rapport with the village administrators.

Table 11

List of Resolution passed Villages

| Sl.No. | Village Name | Union |
| --- | --- | --- |
| 1 | Sillamarathupatty | Bodi |
| 2 | Dombucherri | Bodi |
| 3 | Uppukottai | Bodi |
| 4 | Maniampatty | Bodi |
| 5 | Lakshmipuram | Periyakulam |
| 6 | Jeyamangalam | Periyakulam |
| 7 | Melmangalam | Periyakulam |
| 8 | Vadapudupatty | Periyakulam |
| 9 | Oonjanpatty | Theni |
| 10 | Aranmanaipudur | Theni |
| 11 | Koduvilarpatty | Theni |

Finance and Administration

The financial support for the activities at the center level was acquired from head office by submitting the budget every month. The activities were carried out without pending by timely support of the administration. Major equipments and materials purchase was directly undertaken by the head office for example, lab consumables, doctor kits etc. The work plan activity wise expenses spent in centre portrayed in the following chart ( The expenses incurred by project staff for travel, food and accommodation(Chennai), Compensation for respondents of BLS and monthly office rent are not included).               Chart 1

Work plan activity wise expenses

Challenges

- Hard to recruit staff for outreach work from the community.

- Delay in permission from TNSACS for testing and accreditation.

- Tough to mobilize target communities to access the services.

Major Activities Planned for the Next Year

- Development of ethical guidelines and policy framework for service providers.

- Development and distribution of IEC materials.

- Organize local network meeting of self help groups of target communities to develop a plan of action to identify and address stigma and discrimination, educate public and seek legal redress when necessary.

- Translation of baseline survey reports in local language.

- Organize workshops for dissemination of reports on stigma and discrimination, meetings for follow up.

- Quarterly network meetings/workshops for local issues.

- Development and translation of training materials and organize training program for care providers.

- Monitoring availability and quality of treatment at government hospitals and adherence to universal precautions (PEP).