Proposal for Evaluation of APAC VCTCs

Background:

APAC has been supporting 22 NGOs in both IIDs and non- IIDs with the VCTC component from October ’07. The primary activities of the VCTC were to provide counselling and testing for core and vulnerable populations such as female sex workers, MSM, IDUs, migrants, industrial workers, truckers in the respective districts. APAC provided both financial as well as technical support to the NGOs. During the first quarter of the project, APAC trained all the counsellors on the counselling module prescribed by NACO with technical assistance from South India AIDS Action Programme (Siaap). All the lab technicians were given an orientation on HIV testing kits and universal precautions. Kits for HIV testing was procured from TANSACS.

The VCTCs were monitored by the District Program Officers (DPOs) on a monthly basis. All VCTCs sent their monthly technical reports (MTRs) which were scrutinized by the technical officer at APAC and the feedback on the same was given to VCTCs through telephone and e-mail. A copy of the consolidated management information systems (CMIS) report was sent to TANSACS. The technical officer also visited some of the VCTCs and suggested mid- course corrections in counselling, documentation, UBP and overall maintenance of the infrastructure.

Present status: NACO has suggested to APAC to close down all its VCTC activities from September 30th 2008 due to the following reasons:

- NACO does not encourage NGO-based VCTCs, when ICTCs are established in every district.

- There is underutilization of ICTCs by NGOs.

- All NGO-based VCTCs should be closed down in Tamil Nadu and clients to be referred only to ICTCs established by the government.

Therefore, by taking the suggestion forward, APAC has decided to close all its VCTC activities and will work out a mechanism with the ICTCs at the respective districts.

APAC would like to undertake an evaluation of all the VCTCs before its closure. All VCTCs will be graded and ranked based on the performance. Further, a process documentation will be undertaken to capture the effectiveness of the NGO based VCTCs for future reference and to share the experience with other national and international agencies.

Siaap’s Experience:

Siaap had partnered with APAC between 2005 and 2007 to build capacity, guide, monitor, evaluate and report on 31 VCTCs established by NGOs and private hospitals in Tamil Nadu and Puducherry with financial support from APAC. Siaap had provided 15 days counselling training to all counsellors. In addition, Siaap staff undertook site visits every month to observe counselling sessions and provide feedback about the quality of counselling services. On certain occasions, the Siaap supervisor would role-model by taking on the role of a counsellor with clients visiting the centre. Siaap staff would also interact with the NGO Director, the Project Coordinator of the NGO the outreach team and the doctor to ensure common understanding and ownership of the VCT project. Documentation was also checked during these visits and doubts clarified.

Besides, Siaap developed an MIS and received the MTRs from all the VCTCs once every month. Corrections were carried out by the NGOs based on feedback provided by Siaap. One consolidated report was then sent to APAC every month regarding data. Siaap also designed the formats for registers, counselling, case studies, verbatim, data management. NGO Teams were assisted with strategies to reach their targets, generate demand and increase collaboration with other interventions being carried out by the NGO. Interpersonal issues too were ironed out during these visits.

Siaap staff facilitated zonal meetings, once every month for the VCTC teams comprising of 2 counsellors and a laboratory technician. Issues related to counselling, testing and data management were discussed. It provided a platform for teams to share their experiences, learn from one another and bring immediate corrections, wherever required. This also created a sense of bonding among all VCTC staff and a spirit of cooperation.

Towards the end of this period, Siaap also arranged exposure visits for all VCTC teams to Karnataka in order to learn from the experiences of another state. This was useful in seeing and learning from other models such as Well Women’s Clinic, Care Centre for PLHA, General Outpatient Clinic (which is a public-private partnership) for PLHA as well as being able to appreciate the programme in one’s own state.

Evaluation Proposal:

Objective:

Siaap proposes to undertake evaluation of 22 APAC supported NGO-based VCTCs, of which 14 are in the Intensive Intervention Districts (IIDs) and 8 in the Non-Intensive Intervention Districts (NIIDs). The chief objectives are:

- Evaluate 22 VCTCs based on pre-determined criteria

- Prepare a process document in relation to NGO-based VCTCs

The process of the VCTC evaluation will include the following:

- Development of tool by the external agency.

- Interaction with team at the respective VCTCs.

- Review of registers/ MTRs.

- Discussion with project holder and NGO staff.

- Observation of counselling session.

- Review of UBP procedures followed in the VCTC.

- Follow- up of positive clients.

- Grading and ranking VCTCs.

- Preparation and submission of evaluation report.

Deliverables:

The following are the expected outcomes from the evaluation:

- Evaluation report pertaining to 22 VCTCs

- Process documentation of NGO-based VCTCs

Parameters for evaluation:

The VCTs will be graded according to the following parameters:

- Technical:

- Review of registers maintained by the VCT i.e. case register, positive clients register, follow-up register, referral registers, case study registers and lab kit registers etc.

- Number of MARPS and vulnerable population tested. Achievement against target.

- Undertake field visits to camp sites and home visits to validate data if necessary.

- Availability of condoms, test kits, lab consumables, etc.

- Ensuring the quality assurance of testing with the regional Medical College Hospitals (EQAS Centre).

- Infrastructure of the center

- Visibility of name board of the VCT center

- Cleanliness of the VCT

- Display of appropriate IEC materials/ posters

- Display of referral centers such as ART/ ICTC/ DOT centers etc

- Availability of safe drinking water

- Clean toilets with running water

- Availability of condoms

- Availability of newspapers/ magazines for clients

- Documentation

- Display of flowchart describing the process of counselling and testing

- Display of  a graphical representation of targets achieved  every month

- Maintenance and updating registers and files

- Laboratory

- Display of UBP materials

- Availability of kits, lab consumables etc.

- Thermostat of the refrigerator set as per the standards

- Disposing waste materials as per the national guidelines

- Visibility of VCT

- Community Involvement in the VCT

- Awareness of the general community / target community of the VCT

- Client’s satisfaction of the C&T process.

Timeline:

- August  - September 2008

Total Estimated Cost:

- Rs. ________